## Week 1
PROJECT REPORT
Group | <SOS>
Week | <09/05/2022-15/05/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Introduction overview | Completed
2 | Context Diagram (SRS) | Completed
3 | Screen flow | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Introduction overview | Hải Nam
2 | Context Diagram | Ngọc Bảo
3 | Screen flow | Ngọc Long, Quang Khải
4 | Report | Quang Khải
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Screen detail
2 | User authorization
3 | Non-Screen function
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
N/A
N/A
N/A
N/A
N/A

## Week 2
PROJECT REPORT
Group | <SOS>
Week | <16/05/2022-22/05/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Edit Screen flow | Completed
2 | Edit Context Diagram | Completed
3 | Product Backlog | In Progress
4 | SRS Part I | Completed
5 | Entity relationship diagram | Completed
6 | Web Skeleton | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Edit Screen flow | Hải Nam
2 | Edit Context Diagram | Ngọc Bảo, Hải Nam
3 | Product Backlog | Ngọc Long, Quang Khải
4 | SRS Part I | Ngọc Bảo
5 | Entity relationship diagram | Quang Khải
6 | Web Skeleton | Ngọc Long
7 | Weekly Report | Quang Khải
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Add Freelance Job topic to Lost and Found | Pending
2 | Edit ERD, SRS file, Backlog file again | Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Edit ERD | 23/05/2022
2 | Complete SRS file | 24/05/2022
3 | Complete Product Backlog file | 24/05/2022
4 | Design Wireframe | 25/05/2022
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | Add more functions about Freelance Job
N/A
N/A
N/A
N/A

## Week 3
PROJECT REPORT
Group | <SOS>
Week | <23/05/2022-29/05/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Edit Screen flow again | Completed
2 | Edit ERD again | Completed
3 | Complete Product Backlog | Completed
4 | Complete SRS Document | In Progress
5 | Design Wireframe | Completed
6 | Code Iteration 1 | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Edit Screen flow again | Hải Nam
2 | Edit ERD | Ngọc Bảo, Quang Khải
3 | Complete Product Backlog | Ngọc Long, Hải Nam
4 | Complete SRS | Ngọc Bảo, Hải Nam
5 | Design Wireframe | Ngọc Long
6 | Report | Quang Khải
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Unfinished SRS document | In Progress
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Code Iteration 1 | 2022-06-04
2 | Design Document
3 | Functional Requirement - SRS Document | 2022-06-01
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | Add user: Employer
N/A
N/A
N/A
N/A

## Week 4
PROJECT REPORT
Group | <SOS>
Week | <30/05/2022-05/06/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Code Iteration 1 | In Progress
2 | Design Document | In Progress
3 | Functional Requirement - SRS Document | In Progress
4 | Find Template | In Progress
5 | Design Database | In Progress
6 |  | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Code Iteration 1 | Team
2 | Design Document | Ngọc Long, Quang Khải, Hải Nam
3 | Functional Requirement - SRS Document | Ngọc Bảo, Quang Khải
4 | Find Template | Ngọc Long, Hải Nam
5 | Design Database | Ngọc Bảo
6 | Report | Quang Khải
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
| Unfinished SRS document | In Progress
| Unfinished Code iteration 1 | In Progress
| Problem with github | Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Complete the function of Interation 1 | 2022-06-10
2 | Edit Template |  | In Progress
3 | Complete SRS Document | 2022-06-12
4 | Design Docment |  | In Progress
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
N/A
N/A
N/A
N/A
N/A

## Week 5
PROJECT REPORT
Group | <SOS>
Week | <06/06/2022-12/06/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Complete Code Iteration 1 | In Progress
2 | SRS Document | In Progress
3 | Design Document | In Progress
4 | Code Interation 2 | In Progress
5 |  | In Progress
6 |  | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Complete Code Interation 1 | Team
2 | SRS Document | Ngọc Bảo, Quang Khải
3 | Design Document | Ngọc Long, Hải Nam
4 | Code Interation 2 | Team
5 | Report | Quang Khải
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
| There are many bugs during project execution | In Progress
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Code Iteration 2 |  | In Progress
2 | Continute Design Document |  | In Progress
3
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
N/A
N/A
N/A
N/A
N/A

## Week 6
PROJECT REPORT
Group | <SOS>
Week | <13/06/2022-19/06/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Code Iteration 1 &2 | In Progress
2 | SRS Document | In Progress | Part II unfinished
3 | Design Document | In Progress
4 | Design conflow | In Progress
5 | Edit Template | In Progress | Find and edit template for Freelance Job
6 |  | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Code Iteration 1 &2 | Team
2 | SRS Document | Ngọc Bảo, Quang Khải
3 | Design Document | Ngọc Long, Hải Nam
4 | Design conflow | Quang Khải,Hải Nam
5 | Edit Template | Ngọc Long,Ngọc Bảo
6 | Report | Quang Khải
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Unfinished Code Iteration 1 | In Progress | There are many bugs and problems using github
2 | Take a long time in editing the template | In Progress
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Complete Code Iteration 1
2 | Complete SRS Document | 2022-06-20
3 | Complete Design Document | 2022-06-24
4 | Code Iteration 2 & 3
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
N/A
N/A
N/A
N/A
N/A

## Week 7
PROJECT REPORT
Group | <SOS>
Week | <20/06/2022-26/06/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Code Iteration 2 & 3 | In Progress
2 | Design Document | In Progress
3 | Edit Template | In Progress | Find and edit template for Freelance Job
4 |  | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Code Iteration 2&3 | Team
2 | Design Document | Ngọc Long, Hải Nam
3 | Edit Template | Ngọc Bảo, Quang Khải
4 | Report | Quang Khải
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Unfinished Code Iteration 2 & 3 | In Progress
2 | Edit template | In Progress | Take a long time in editing the template
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Complete Code Iteration 2 & 3
2 | Complete Design Document | 2022-07-01
3
4
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
N/A
N/A
N/A
N/A
N/A

## Week 8
PROJECT REPORT
Group | <SOS>
Week | <27/06/2022-03/07/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Code Iteration 3 | In Progress
2 | Design Document | In Progress
3 |  | In Progress
4 |  | In Progress
5 |  | In Progress
6 |  | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Code Iteration 3 | Team
2 | Design Document | Ngọc Long, Hải Nam
3
4
5
6 | Report | Quang Khải
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 |  | In Progress
2 |  | In Progress
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1
2
3
4
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
N/A
N/A
N/A
N/A
N/A