## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
List all post + Paging + Show more | Post Management | Simple | Iteration 1 | SE150650 | Trịnh Ngọc Bảo
Show your post | Post Management | Medium | Iteration 2 | SE150650 | Trịnh Ngọc Bảo
Search post | Post Management | Simple | Iteration 1 | SE150823 | Tăng Quang Khải
Upload Post | Post Management | Medium | Iteration 2 | SE150823 | Tăng Quang Khải
Delete Post | Post Management | Simple | Iteration 1 | SE150888 | Phạm Ngọc Long
Delete reported post | Post Management | Medium | Iteration 2 | SE150888 | Phạm Ngọc Long
Edit Post | Post Management | Medium | Iteration 1 | SE150888 | Phạm Ngọc Long
View detail | Post Management | Medium | Iteration 2 | SE150650 | Trịnh Ngọc Bảo
View statistics | View | Medium | Iteration 3 | SE150650 | Trịnh Ngọc Bảo
Admin Dashboard | Post Management | Medium | Iteration 2 | SE150925 | Nguyễn Văn Hải Nam
User Dashboard | Post Management | Medium | Iteration 2 | SE150888 | Phạm Ngọc Long
Approve post | Post Management | Medium | Iteration 2 | SE150823 | Tăng Quang Khải
Edit user profile | User Management | Medium | Iteration 2 | SE150823 | Tăng Quang Khải
View information of user | User Management | Medium | Iteration 2 | SE150888 | Phạm Ngọc Long
Remove user | User Management | Simple | Iteration 2 | SE150650 | Trịnh Ngọc Bảo
Login | Account | Medium | Iteration 1 | SE150925 | Nguyễn Văn Hải Nam
Logout | Account | Simple | Iteration 1 | SE150925 | Nguyễn Văn Hải Nam
Register | Account | Medium | Iteration 1 | SE150925 | Nguyễn Văn Hải Nam
Change password | Account | Simple | Iteration 1 | SE150925 | Nguyễn Văn Hải Nam
List category | Category Management | Medium | Iteration 2 | SE150823 | Tăng Quang Khải
Search category | Category Management | Simple | Iteration 2 | SE150888 | Phạm Ngọc Long
Add category | Category Management | Medium | Iteration 2 | SE150888 | Phạm Ngọc Long
Edit category | Category Management | Simple | Iteration 1 | SE150888 | Phạm Ngọc Long
Send report | Report Management | Simple | Iteration 2 | SE150650 | Trịnh Ngọc Bảo
View report | Report Management | Medium | Iteration 3 | SE150650 | Trịnh Ngọc Bảo
Submit feedback | Feedback Management | Medium | Iteration 2 | SE150925 | Nguyễn Văn Hải Nam
View feedback | Feedback Management | Medium | Iteration 3 | SE150925 | Nguyễn Văn Hải Nam
Send mail | Email | Simple | Iteration 3 | SE150823 | Tăng Quang Khải
Call | Phone Call | Simple | Iteration 3 | SE150823 | Tăng Quang Khải
Upload Job Post | Job Management | Simple | Iteration 3 | SE150925 | Nguyễn Văn Hải Nam
Approve Freelance Job Post | Job Management | Simple | Iteration 3 | SE150925 | Nguyễn Văn Hải Nam
List Job Post | Job Management | Simple | Iteration 3 | SE150823 | Tăng Quang Khải
List User Job | Job Management | Simple | Iteration 3 | SE150823 | Tăng Quang Khải
Details Job Post | Job Management | Simple | Iteration 3 | SE150650 | Trịnh Ngọc Bảo
Submit Form | Job Registration | Medium | Iteration 3 | SE150650 | Trịnh Ngọc Bảo
List User Apply | Job Management | Medium | Iteration 3 | SE150925 | Nguyễn Văn Hải Nam
List User Approve | Job Management | Medium | Iteration 3 | SE150925 | Nguyễn Văn Hải Nam
Employer profile | User Management | Simple | Iteration 3 | SE150888 | Phạm Ngọc Long
Employer Dashboard | Job Management | Medium | Iteration 3 | SE150823 | Tăng Quang Khải
List jobs currently hiring | Job Management | Simple | Iteration 3 | SE150650 | Trịnh Ngọc Bảo
List done job | Job Management | Simple | Iteration 3 | SE150650 | Trịnh Ngọc Bảo
Upload job post | Job Management | Medium | Iteration 3 | SE150823 | Tăng Quang Khải
Freelancer profile | User Management | Simple | Iteration 3 | SE150888 | Phạm Ngọc Long
Delete job post | Job Management | Simple | Iteration 3 | SE150823 | Tăng Quang Khải
Edit job post | Job Management | Simple | Iteration 3 | SE150823 | Tăng Quang Khải
View all category of freelance job | Category Job Management | Simple | Iteration 3 | SE150888 | Phạm Ngọc Long
Add category of freelance job | Category Job Management | Simple | Iteration 3 | SE150888 | Phạm Ngọc Long
Delete category of freelance job | Category Job Management | Simple | Iteration 3 | SE150888 | Phạm Ngọc Long
Search category of freelance job | Category Job Management | Simple | Iteration 3 | SE150925 | Nguyễn Văn Hải Nam
View applied job | Job Management | Medium | Iteration 3 | SE150925 | Nguyễn Văn Hải Nam
Edit employer profile | User Management | Medium | Iteration 3 | SE150650 | Trịnh Ngọc Bảo
Edit freelancer profile | User Management | Medium | Iteration 3 | SE150650 | Trịnh Ngọc Bảo